## myCardioMEMs Timeline
CMEMS | MyCardioMEMS
|  | Planned Completion Date | Actual / Expected Completion Date | Comments/Status | Dependency
Documentation | SRS Document
Technical Specification
Design Document
Impact Analysis
Task Management | JIRA task management strategy
Create EPIC, Stories and Tasks
Backlog grooming
Assign Tasks
SCM | Branching Strategy
Set up Branches in Bitbucket
Review Branching strategy and code review process
Artifactory set up | set up Artifactory
Build Agent & Server Set up | set up build agent
Create Service Connection to Bitbucket
Install Xcode in MacOS Agent
Build | Install XCPretty in MacOS Agent
Add Task - Archive the application build Locally with CLI
Add Task - Export the Application Archive Locally with CLI
Create a new build pipeline on Azure DevOps
Implementing the xcode build automate on Azure DevOps
Add Task - Install Apple Certificate
Add Task - Install Apple Provisioning Profile
Add Task - Xcode Agent task
Build the application with xcodebuild
Add Task - XCTest unit Framework
Integrate and Configure Coverity
Integrate and Configure Azure Artifacts
Publishing to Aritifact Server
Continuous Deployment | Create CD Pipeline in Azure DevOps
Fetch Release Package from Artifact
| Integration Test automation framework |  |  |  | Hari Vemuri / Sathish Kanniah
| Configure App Store Connect |  |  |  | Schdeule meeting with Kevin
| Publish Release Bundle to App Store Connect |  |  |  | Schdeule meeting with Kevin
Get Business Signoff or validation
Windchill Release | Create Doc ID |  |  |  | Understand Windchill release process and get needed access
Create CO for Verification Report
Create CO Validation Report
Formal Release
System Access Required | Bitbucket Access
Azure DevOps Account Access
Coverity Configure
Coverity Access
Self-hosted agent Server access
Infra as a Code | Create Playbook
Deploy Playbook
Prod Support | Prod deployment Support
Note on C34: Gunturu, Chandrasekhar: Add my mac as an agent to do the builds
Note on C35: Gunturu, Chandrasekhar: Add my mac as an agent to do the builds

## HMT Timeline
HMT | Task Id | QA Tested | Heart Mate Touch | Acceptance Criteria/Deliverables Checkpoints | Reviewed By | Review/Comments | Status | HCL/ Abbott/ HCL & Abbott | Remarks
[10 empty] | Planned Completion Date | Actual / Expected Completion Date | Comments/Status | Dependency
Documentation |  |  | SRS Document | [6 empty] | verification In-Progress
Technical Specification
Design Document
Impact Analysis
Task Management |  |  | JIRA task management strategy | [6 empty] | N/A for now(Checking with Nate)
Create EPIC, Stories and Tasks
Backlog grooming
Assign Tasks
SCM |  |  | Branching Strategy | [6 empty] | (Conformation from Nate is needed) |  |  | Branching Strategy has been discussed with Nate. Nate is working on cleanup and we cloned the Translations branch for the build pipeline for now and will follow the braching strategy once it has be reviewed and finalized.
|  |  | Set up Branches in Bitbucket | [6 empty] | (Conformation from Nate is needed)
|  |  | Review Branching strategy and code review process | [6 empty] | (Conformation from Nate is needed)
Artifactory set up |  |  | set up Artifactory | [6 empty] | Will be using Azure Atrifactory
Build Agent & Server Set up |  |  | set up build agent | [6 empty] | 2022-04-04 | 2022-05-20 | Completed | macOS should be available, this is resolved now
|  |  | Create Service Connection to Bitbucket | [6 empty] | 2022-04-04 | 2022-05-20 | Completed
|  |  | Install Xcode in MacOS Agent | [6 empty] | 2022-04-04 | 2022-05-20 | Completed
Build |  |  | Install XCPretty in MacOS Agent | [6 empty] | 2022-04-04 | 2022-05-20 | Completed
|  |  | Add Task - Archive the application build Locally with CLI | [6 empty] | 2022-05-23 | 2022-05-24 | Completed
|  |  | Add Task - Export the Application Archive Locally with CLI | [6 empty] | 2022-05-24 | 2022-05-24 | Completed
|  |  | Create a new build pipeline on Azure DevOps | [6 empty] | 2022-06-01 | 2022-05-31 | Completed | Branching Strategy and feature branch clean up is required.
|  |  | Implementing the initial xcode build automate on Azure DevOps | [6 empty] | 2022-06-01 |  | Completed | Apple developer account and provisioning profile is required.(Completed)
|  |  | Add Task - Install Apple Certificate | [6 empty] | 2022-06-10 | 2022-06-06 | Completed
|  |  | Add Task - Install Apple Provisioning Profile | [6 empty] | 2022-06-11 | 2022-06-08 | completed
|  |  | Add Task - Xcode Agent task | [6 empty] | 2022-06-12 | 2022-06-08 | Completed
|  |  | Cocoa Pods (Pod install) task | [6 empty] | 2022-06-12 | 2022-06-08 | completed
|  |  | Build the application with Command line interface( Archive,build) | [6 empty] | 2022-06-13 | 2022-06-10 | Completed
|  |  | Build the application with Xcode( Pod install,Archive,build,test) | [6 empty] | 2022-06-17 | 2022-06-09 | in progress
|  |  | Add Task - XCTest unit Framework(Check with birajan) | [6 empty] | 2022-06-15 | In Progress | In progress ( working with developers to troubleshoot the test issues) | Development Team Investigating the few unit test cases that are failing. Birajan will take up this task as there are other priorties that he need to take care of now.
|  |  | Integrate and Configure Coverity | [6 empty] | 2022-06-25 | Investigate
|  |  | Integrate and Configure Azure Artifacts | [6 empty] | 2022-06-12 | 2022-06-06 | Completed
|  |  | Publishing to Aritifact Server | [6 empty] | TBD
Continuous Deployment |  |  | Create CD Pipeline in Azure DevOps | [6 empty] | 2022-06-20
|  |  | Fetch Release Package from Artifact | [6 empty] | 2022-06-20
|  |  | Integration Test automation framework | [6 empty] | TBD |  |  | Hari Vemuri / Sathish Kanniah
|  |  | Configure App Store Connect | [6 empty] | TBD |  |  | Scheduled a meeting Kevin on June 13th to understand the App Release process with TestFlight
|  |  | Publish Release Bundle to App Store Connect | [6 empty] | TBD
|  |  | Get Business Signoff or validation | [6 empty] | TBD
Windchill Release |  |  | Create Doc ID | [6 empty] | 2022-03-05 |  |  | Understand Windchill release process and get needed access - TBD
|  |  | Create CO for Verification Report | [6 empty] | TBD
|  |  | Create CO Validation Report | [6 empty] | TBD
|  |  | Formal Release | [6 empty] | TBD
System Access Required |  |  | Bitbucket Access | [6 empty] | Completed
|  |  | Azure DevOps Account Access | [6 empty] | Completed
|  |  | Coverity Configure | [6 empty] | 2022-03-15
|  |  | Coverity Access | [6 empty] | 2022-03-20
|  |  | Self-hosted agent Server access | [6 empty] | 2022-02-28
Infra as a Code |  |  | Create Playbook | [6 empty] | TBD
|  |  | Deploy Playbook | [6 empty] | TBD
Prod Support |  |  | Prod deployment Support | [6 empty] | TBD
Note on K34: Gunturu, Chandrasekhar: Add my mac as an agent to do the builds
Note on K39: Gunturu, Chandrasekhar: Add my mac as an agent to do the builds

## HMT Projection (hidden)
Workstream Milestones | Plan End Date | Actual / Expected Date | Status
Understanding current system and getting Abbott Id and access to Abbott Systems(Bitbucket, Azure DevOps, Jira) | 2021-11-19 | 2021-11-19
2021-12-01
2021-12-03
Create Project and scrum board in Jira, Integrating Bitbucket with Azure DevOps Repo | 2021-11-26 | 2021-11-26
2021-11-30
Create Continuous Integration in Azure DevOps pipeline in Dev environment and build project using XCode build agent. | 2021-12-03 | 2021-12-03
2021-12-02
2021-12-10
2021-12-17
Integrating Unit Test framework XCTest in CI Pipeline | 2022-01-25
Getting Crypto Keys for Signing in Dev and Install Certificates Integrate and Configure SonarQube and Jfrog artifactory Publishing to Aritifact Server | 2022-01-30
Creating Continuous Deployment in Azure DevOps pipeline and deploy to App Store Connect with signing image
Create IAC code to create and deploy infrastructure | 2021-12-31 | 2021-12-31
Deploy infrastructure and pipeline using IAC | 2022-01-07 | 2022-01-07
Prepare CI and CD pipeline to Deploy / Distribute in Prod environment | 2022-01-14 | 2022-01-14
Support Pre and Post Prod Deployment | 2022-01-21 | 2022-01-21